NYS Community Reconstruction Zone

Planning Program

The New York State Community Reconstruction Zone (CRZ) Program was established to provide additional rebuilding and revitalization assistance to communities severely damaged by Hurricanes Sandy and Irene and Tropical Storm Lee. To facilitate community redevelopment planning and the resilience of communities, the State has established the Community Reconstruction Zone (CRZ) Program and has allocated up to $25 million in planning grants for the most affected communities. Later allocations of funds will be used to support the implementation of projects and activities identified in the CRZ Plans that the identified communities will produce.

The CRZ Planning Program will allow communities to identify safe, resilient, and innovative   reconstruction projects based on community-driven plans that consider current damage, future threats, and the community’s economic opportunities.

Each identified community will convene a CRZ Planning Committee that includes, among others, a representative from the County, Town or Village, elected legislative representatives, local residents, and directors of established organizations and businesses in the community. The CRZ Planning Committee will be responsible for developing the content of the CRZ Plan. The State will provide a variety of consultants to assist in the development of CRZ Plans.

PLANNING ASSISTANCE

The State is providing each designated CRZ Community with a planning consultant team to help them prepare a community reconstruction zone plan. The consultants will be hired through a State RFP process administered by New York State Homes and Community Renewal (NYS HCR) through its Office of Community Renewal (OCR) and the Housing Trust Fund Corporation (HTFC).

Planning experts from either the Department of State or Department of Transportation will be assigned to each CRZ Community to provide assistance and to help manage the planning consultant.

PLANNING STEPS

The CRZ Plan will provide a list of projects and actions needed for the community to recover, improve its economy, and reduce future natural disaster damage. Development of a successful plan will qualify a community to receive federal funding to implement the identified projects. The planning process will include the following important steps:

• Public Engagement: Offering opportunities for public input and involvement at key milestones in the planning process.

• Asset Inventory: Completing a detailed inventory of the community’s social, economic, and natural resource assets and systems that have been, or will be, affected by coastal or riverine hazards.

• Risk Assessment: Assessing risk to key community assets and systems based on the three factors contributing to risk:

– Hazard: The likelihood and magnitude of anticipated hazard events.

– Exposure: Local landscape characteristics that tend to increase or decrease storm effects.

– Vulnerability: The capacity of an asset or system to return to service after an event.

• Needs and Opportunities Assessment: Determining needs and opportunities to improve local economic growth and development and enhance resilience to future storms.

• Strategies for Investment and Action: Developing strategies and identifying projects and actions needed to implement the strategies; identifying potential costs and benefits of chosen projects and actions, as well as potential funding sources.

• Implementation Schedule: Preparing a detailed implementation schedule of the actions the community will take to implement the strategies in the CRZ Plan, including the timeline for completing each action and the party responsible for the action.

In addition to developing CRZ plans, communities on Long Island will develop a regional plan for redevelopment and resilience, led by the Long Island Regional Planning and Economic Development Council (LIREDC).

TIMEFRAME

The planning process is expected to take approximately 8 months. Thus, if the process kicks off at the beginning of July, the completed plans should be submitted to the state by the end of January for review, and if necessary, revised and final plans submitted by the end of February.

Interim goals have been established in recognition of the one year anniversary of Hurricane Sandy.  By October 30, all CRZs should have a conceptual plan prepared containing draft key strategies, actions, and/or projects.

PLAN CONTENTS

Development of a plan which contains the required elements will qualify a community to receive implementation grants and guide long term construction and use of other federal, state, local, nonprofit funds and private sector investments. The CRZ Plan will result in a list of projects and actions needed for the community to recover and to reduce future hazard damages. The community will estimate costs and benefits of the proposed course of action, and set priorities for the projects that have the most significant value.

The items that must be contained in a CRZ Plan are listed below:

Transmittal Letter

Overview

• Geographic Scope of Plan

• Description of Storm Damage

• Critical Issues

• Community Goals

• Relationship to Regional Plans

Assessment of Risk and Needs

• Community Assets

• Assessment of Risk to Assets

• Assessment of Risk to Systems

• Assessment of Needs and Opportunities

Reconstruction Strategies

• Community Planning and Capacity Building

• Economic Development

• Health and Social Services

• Housing

• Infrastructure

• Natural and Cultural Resources

Implementation Schedule

• Schedule of Implementation Actions

Appendices

• List of CRZ Planning Committee Members

• Description of Public Engagement Process

• Description of Priority Projects and their Costs and

Benefits

• Inventory of Assets

CHARACTERISTICS OF A SUCCESSFUL CRZ PLAN

To qualify for grants to implement a CRZ Plan, the plan must include the following characteristics:

• Assessment of risk to key assets and systems. As the bedrock of the plan, an inventory of the vulnerabilities of key assets and systems is necessary to prioritize various projects and actions.

• Projects and actions to restore and increase the resilience of key assets. The CRZ Plan should address both the restoration of key assets and actions that will make them more resilient to future threats. Examples of such projects and actions include restoration or mitigation of natural infrastructure (e.g. wetlands, oyster reefs, dunes, and other green infrastructure), changes in land use regulations (e.g. changes in use, increased setbacks, and transfer of density) to encourage sound development, and investments in transportation or other improvements in community systems to prepare for future threats.

• Protection of vulnerable populations. The CRZ Planning Committee should develop new measures to protect vulnerable persons (people with disabilities, low and very-low income populations, elderly, young children, homeless and people at risk of becoming homeless) through housing decisions and other services. For example, site new facilities in lower risk areas, require backup power systems for critical facilities such as nursing homes and hospitals, and improve communications systems to ensure that vulnerable persons are not left without aid. Some actions to address vulnerable populations could include amendments to municipal emergency management procedures.

• Projects with economic growth co-benefits. Projects that will improve the future of the local economy may also enhance the resilience of the community. For example, investments in new transportation infrastructure may facilitate the growth of Main Street business corridors; and investments in new recreational assets (e.g. new green space that serves as a buffer against coastal flooding) may protect against storm damage or serve as redundant protection in critical areas, while also drawing tourists or facilitating the growth of new businesses.

• Regional coordination. To ensure that CRZ Plans are consistent with regional objectives and that a regional response to the challenges that cross political jurisdictions serve the community’s long-term objectives, Long Island communities and must participate in a regional planning process.

• Detailed implementation agendas. Each CRZ Plan must include a clear and detailed description of the tasks it will take to implement the plan. This includes assigning responsibility for specific actions to specific individuals or organizations, and establishing timelines for each action, as appropriate.